## Moizuddin
WORK LOG - GROUP 3 KNOWLEDGE MANAGEMENT
Date | Day | Meeting | Planned Tasks | Performed Tasks | Goal Achievement Status | Any Submission of Document
2025-03-10 | Monday | Suresh and Jay's Session on Project Processes | Requirement Gathering for the Project, Requirement Analysis and Narrowing Scope | Gathered Requirements, Analysed requirements, set the scope for the project | Achieved | -
2025-03-11 | Tuesday | - | Create User Stories and Technical Stories for the project requirements (WHAT) | Made 11 user stories and 9 Technical stories and estimated time required | Achieved | Submitted Requirements and User Stories Document on Teams
2025-03-12 | Wednesday | - | Make Plan for the project assigning stories to the team and scheduling(WHO and WHEN) | Made Schedule for the project and assigned the stories to the team members added this to 'Project Report' Docx | Achieved | -
2025-03-13 | Thursday |  | 1. Decide on the Technologies and methods of creating the project. (HOW) 2. Retrospect the planning 3. Creating Mock Screen, Themes, Nomenclature | 1. Finalised Technologies for developement 2. Finalised themes names icons mock screens | Achieved
2025-03-14 | Friday

## Kaustubh
WORK LOG - GROUP 3 KNOWLEDGE MANAGEMENT
Date | Day | Meeting | Planned Tasks | Performed Tasks | Goal Achievement Status | Any Submission of Document
2025-03-10 | Monday | Suresh and Jay's Session on Project Processes | Requirement Gathering for the Project, Requirement Analysis and Narrowing Scope | Gathered Requirements, Analysed requirements, set the scope for the project | Achieved | -
2025-03-11 | Tuesday | - | Create User Stories and Technical Stories for the project requirements (WHAT) | Made 11 user stories and 9 Technical stories and estimated time required | Achieved | Submitted Requirements and User Stories Document on Teams
2025-03-12 | Wednesday | - | Make Plan for the project assigning stories to the team and scheduling(WHO and WHEN) | Made Schedule for the project and assigned the stories to the team members added this to 'Project Report' Docx | Achieved | -
2025-03-13 | Thursday |  | 1. Decide on the Technologies and methods of creating the project. (HOW) 2. Retrospect the planning 3. Creating Mock Screen, Themes, Nomenclature | 1. Finalised Technologies for developement 2. Finalised themes names icons mock screens | Achieved
2025-03-14 | Friday